## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (actual date) | Date finished (actual date)
1 | Account Management | As a user, I want to be able to create, modify, manage the status of, modify and validate my account, so that I can ensure my account information is accurate and up-to-date, maintaining data integrity. | high | Sprint 1 | Account Management: Includes account creation, modification, status management, personal information modification, and account verification. | large |  | 2025.3.11
2 | Banking Transaction Services | As a user, I want to be able to perform core banking functions such as deposits, withdrawals, and transfers, so that I can easily manage my financial transactions and meet my basic banking needs. | high | Sprint 1 | Core Banking Services: Enables deposit, withdrawal, and transfer services, and supports transfers between different accounts and basic fund management functions. | large |  | 2025.3.11
3 | Transaction Data Entry: | As a user, I want to be able to manually input my transactions through the user interface, as well as import structured transaction data from CSV files, so that I can quickly and efficiently record my financial activities. | middle | Sprint 2 | Transaction Input: Users can manually input transactions and also support bulk importing of transaction data in CSV file format. The system also provides data validation features. | medium |  | 2025.3.11
4 | Monthly/Annual billing statistics | As a user I want to be able to generate a pie chart to visually show the percentage of monthly or annual financial expenses So that I can quickly identify and assess each expense as a percentage of my total expenditure, helping me make smarter financial decisions. | High | Sprint 1 | 1. Can generate pie charts according to the specified time range. 2. The chart can show the name of each expenditure category and its proportion. 3. Categories of expenditure include but are not limited to: dining, entertainment, shopping, etc. 4. The percentage of expenditure can be clearly displayed by color, label or number. | large |  | 3.11
5 | Bill review | As a user I want to see my billing details, so that I can clearly understand the cost of each billing item, ensure billing accuracy and manage my spending. | High | Sprint 1 | Each bill should clearly show the bill number, the date of the bill, the charges and their details. | medium |  | 3.11
6 | Abnormal consumption real-time monitoring and fast user confirmation | As a user, I want to receive immediate alerts to verify suspicious transactions So that I can prevent fraudulent activities while maintaining a seamless payment experience | medium | Sprint 1 | 1.Make sure reminder alarm be Triggered when transaction amount is larger than 200% of the user’s average monthly spending 2.Send a verification request via in-app push notification within 5 seconds 3.If the user is not authenticated, it is mandatory to change the payment password at the next login | large | Transaction records need to be invoked | 3.13
7 | Forecast of future consumption peak | As a user, I want the system to predict potential future spending peaks so that I can adjust my saving and budgeting strategies in advance. | High | Sprint 1 | 1. The forecast content should include the specific time range (such as Double 11, Spring Festival shopping season, etc.) and likely consumption categories. 2. Users can see the predicted spending peaks and receive suggestions to save accordingly. | medium |  | 3.15
8 | Customize the time period to generate reports | As a user, I want to generate financial reports based on custom time periods (weekly, monthly, or any specific range) so that I can track my income and expenses effectively. | Medium | Sprint 2 | 1. Users can select any time range (e.g. week, month, specific date) to generate financial reports. | large |  | 3.14
9 | Analysis of income, expenditure and savings in reports | As a user, I want the financial report to include my earnings, expenses, and savings trends so that I can make better financial decisions. | High | Sprint 1 | 1. The generated financial report should include an analysis of income, expenditure and savings trends. | large |  | 3.16
10 | Financial report visualization | As a user, I want my financial reports to be visualized with charts and graphs so that I can quickly understand my financial health. | Medium | Sprint 2 | 1. Financial reports can be visualized on a line chart. | medium |  | 3.17
11 | AI generates a monthly budget | As a user, I want the AI to generate a personalized monthly budget based on my income and past spending habits so that I can manage my finances efficiently and avoid overspending. | Very High | Sprint 1 | 1. AI can generate a personalized monthly budget based on a user's income and historical spending habits. 2. Users can view budget details. | large |  | 3.16
12 | Suggestions for smart savings goals | As a user, I want the AI to recommend appropriate savings goals based on my financial habits and upcoming expenses so that I can systematically grow my savings and achieve my financial objectives. | High | Sprint 2 | 1. The AI can recommend reasonable savings goals based on the user's financial habits and upcoming expenses. 2. Users can adjust suggested savings goals or set up a personalized savings plan. 3. The target recommendation should clearly list the recommended deposit amount, time period and basis. | large |  | 3.15
13 | Cost reduction recommendations based on spending behavior | As a user, I want the AI to analyze my spending patterns and suggest ways to reduce unnecessary expenses so that I can optimize my financial management and increase my savings. | High | Sprint 1 | 1. AI can analyze users' spending patterns and identify possible savings opportunities. | medium |  | 3.18
14 | Consumption close to budget warning | As a user, I want to be alerted when my spending is about to exceed my budget so that I can make informed decisions and adjust my expenses accordingly. | High | Sprint 2 | 1. When the user's consumption is close to the budget, the system should pop up a warning notice in real time. | small |  | 3.18
15 | Query Account Balance via Natural Language | As a user, I want to query my current account balance using natural language , so that I can quickly understand my financial situation. | Must have | 1 | 1. System correctly returns the current balance upon query. 2. Clearly handles ambiguous queries and provides helpful guidance. | small | Core functionality | 2025.3.13
16 | Query Time-specific Expenses via Natural Language | As a user, I would like to use natural language to look up my total expenses and specific expense categories for a particular period of time, so that I can manage my finances better. | Must have | 1 | 1. System returns total expense upon user's request. 2. System provides detailed breakdown by spending category when requested. | medium | Core functionality | 2025.3.13
17 | AI Assistant Provides Saving Recommendations | As a user, I want the AI assistant to analyze my spending patterns and provide saving recommendations via natural language, so that I can make smarter financial decisions. | Should have | 2 | 1. AI analyzes historical data and clearly communicates actionable saving advice. 2. Recommendations are specific, understandable, and relevant. | extra large | Enhancement | 2025.3.14
18 | Record Transactions via Speech/Text Input | As a user, I want to record new transactions quickly via speech or text input, so that I don't need to enter transactions manually. | Must have | 2 | 1. System accurately captures date, amount, and category from user's input. 2. User receives confirmation or prompt to complete incomplete entries. | medium | Core functionality | 2025.3.15